Project Riverside — Project Plan

Larkfield IT  ·  Version 3 (FINAL)

| Version | 3 — FINAL |
| --- | --- |
| Date | September 30, 2026 |
| Plan owner | Jordan Ellis, IT Project Coordinator |
| Approved by | Dana Whitfield, IT Director (approved 9/30/2026) |
| Exec sponsor | Elaine Brooks, COO |

# 1. Overview

Project Riverside moves Larkfield Home Goods headquarters (about 180 staff) from 400 Main Street to our new office at Riverside Commons, floors 2 and 3. IT is responsible for getting the new space wired, secured and ready so that everyone can log in and work normally on their first morning at Riverside.

As part of Riverside we are also retiring the shared help desk mailbox (helpdesk@larkfield.example) and replacing it with HelpRoute, a hosted ticketing service. HelpRoute goes live before the move so that move-related requests are tracked in one place.

# 2. Scope

In scope

Structured cabling and switching at Riverside: 220 Cat6A drops and 8 PoE switches (NetLink Cabling Partners).

Wi-Fi for staff and guests on floors 2 and 3.

Badge access: 14 badge readers and 2 controllers (Keystone Access Systems).

Disconnect, crate, move and reconnect of all workstations, monitors, docks and printers (Swift Crate Movers, IT crating).

HelpRoute setup, help desk training and production cutover.

Pickup and certified disposal of retired equipment (ReCircuit IT Asset Disposal).

Day-1 floor support at Riverside.

Out of scope

Furniture, fit-out, parking and building amenities (Facilities — Hank Delacroix).

Phone system replacement (separate FY27 project).

Changes to line-of-business applications.

# 3. Milestones

| # | Milestone | Date | Owner | Status |
| --- | --- | --- | --- | --- |
| 1 | Vendor selection complete | Fri Sep 25 | Jordan Ellis | Done |
| 2 | Old equipment pickup (ReCircuit) | Wed Oct 14 | Tomás Ferreira | Scheduled |
| 3 | HelpRoute staff training | Tue–Thu Oct 27–29 | Priya Raman | Planned |
| 4 | HelpRoute production cutover | Mon Nov 2 | Priya Raman | Planned |
| 5 | Keystone badge reader install (14 readers, 2 controllers) | Mon–Wed Nov 9–11 | Marcus Oyelaran | Planned |
| 6 | NetLink cabling + PoE switches at Riverside | Thu–Mon Nov 12–16 | Marcus Oyelaran | Planned |
| 7 | Move weekend (Swift Crate Movers) | Sat–Sun Nov 21–22 | Jordan Ellis | Planned |
| 8 | Day-1 support at Riverside | Mon Nov 23 | Priya Raman | Planned |

All dates are 2026.

# 4. Roles

| Name | Role | Riverside responsibility |
| --- | --- | --- |
| Elaine Brooks | COO | Executive sponsor; final call on dates and budget |
| Dana Whitfield | IT Director | Leads Riverside IT work; approves plan and changes |
| Jordan Ellis | IT Project Coordinator | Plan owner; vendor contact; keeps the shared drive |
| Marcus Oyelaran | Network & Infrastructure Lead | Cabling, switches, Wi-Fi, badge access |
| Priya Raman | Help Desk Lead | HelpRoute rollout; Day-1 support |
| Tomás Ferreira | Systems Administrator | Workstation prep, asset tracking, disposal |
| Gloria Mendez | Finance Controller | Budget approvals and POs |
| Hank Delacroix | Facilities Manager | Riverside building management, furniture |
| Simone Adair | HR Manager | All-staff communications |

# 5. Communications

Riverside IT standup every Wednesday, 9:30 AM. Notes go in the meeting notes folder on the shared drive.

Status summary to Elaine Brooks every other Friday (Dana).

All-staff move updates from HR (Simone) at 4 weeks, 2 weeks and 1 week before the move, plus a move-weekend checklist.

Jordan is the single point of contact for all Riverside vendors. Schedule changes go through Jordan.

Support requests go to helpdesk@larkfield.example until the HelpRoute cutover, then to the HelpRoute portal.

# 6. Assumptions

Riverside Commons floors 2–3 are available to Larkfield and our vendors from Mon Nov 2.

Access to 400 Main Street continues through the move weekend (Elaine is confirming the lease wrap-up with the Main St landlord).

Approved budget is $221,300 including $15,000 contingency (see Riverside budget spreadsheet in Planning).

Staff keep their own laptops; desktops, monitors and docks are crated and moved by the movers.

Vendors confirm their dates in writing at least two weeks ahead.