## Budget
Project Riverside — Budget
Last updated 10/9/2026 — JE
Line item | Vendor | Budgeted | Committed | Remaining | Notes
Movers | Swift Crate Movers | 38000 | 0 | 38000 | quote pending
Network cabling | NetLink | 52000 | 49800 | 2200 | SOW signed 10/9 — 220 drops + 8 PoE switches
Badge access | Keystone | 18500 | 18500 | 0 | PO signed — 14 readers, 2 controllers
Help desk software (yr 1) | HelpRoute | 9600 | 9600 | 0 | annual subscription, invoiced 10/1
IT asset disposal | ReCircuit | 3200 | 3200 | 0 | flat fee, pickup sched 10/14
Furniture & fit-out | (Facilities) | 64000 | 58250 | 5750 | Facilities (Hank) tracking
New monitors & docks |  | 21000 | 19480 | 1520 | PO 10/5, delivery ETA ~10/14
Contingency |  | 15000 | 0 | 15000 | Finance approval req'd to use
TOTAL |  | 221300 | 158830 | 62470

## Change log
Date | Change | By
9/18/2026 | Initial budget lines from plan v2 draft; numbers from Gloria | JE
9/30/2026 | Added HelpRoute yr 1 subscription; contingency set at $15,000 per Dana | JE
10/9/2026 | Updated committed: NetLink SOW, Keystone + ReCircuit POs, monitors/docks PO. Movers still $0 - waiting on Swift Crate revised quote after today's walkthrough | JE