Project Riverside — Project Plan

Larkfield IT  ·  Version 2 (draft)

| Version | 2 — DRAFT, not approved |
| --- | --- |
| Date | September 10, 2026 |
| Plan owner | Jordan Ellis, IT Project Coordinator |

# Overview

Move HQ (~180 staff) from 400 Main Street to Riverside Commons floors 2 and 3. Evaluating a ticketing tool to replace the helpdesk@ shared mailbox (HelpRoute is the front runner).

# Draft milestones

| Milestone | Target date | Owner |
| --- | --- | --- |
| Vendor selection complete | Fri Sep 25 | Jordan Ellis |
| Old equipment pickup (ReCircuit) | Mid-Oct, TBD | Tomás Ferreira |
| Help desk ticketing cutover (HelpRoute?) | TBD | Priya Raman |
| Badge reader install | TBD — waiting on Keystone | Marcus Oyelaran |
| Network cabling at Riverside | Mon–Fri Nov 16–20 | Marcus Oyelaran |
| Move weekend | Sat–Sun Dec 5–6 | Jordan Ellis |
| Day-1 support at Riverside | Mon Dec 7 | Priya Raman |

# Open items

Movers — still collecting quotes.

Need budget numbers from Gloria before this goes to Dana for approval.

Confirm floor plan / drop counts with Facilities.