Installation Schedule & Customer Prerequisites

| Customer | Larkfield Home Goods |
| --- | --- |
| Site | Riverside Commons, Floors 2–3 |
| Customer contact | Jordan Ellis, IT Project Coordinator — jordan.ellis@larkfield.example |
| Prepared by | Teresa Vance, Install Coordinator |
| Issued | October 2, 2026 |
| Install dates | Monday–Wednesday, November 9–11, 2026 |

## Equipment

14 badge readers, model KA-R200 multi-technology (8 on Floor 2, 6 on Floor 3)

2 access controllers, model KA-C16 (1 per floor, mounted in the telecom room)

200 programmed staff badges, delivered on Day 3

## Install Schedule

| Day | Date | Work | Crew |
| --- | --- | --- | --- |
| 1 | Mon Nov 9, 2026 | Floor 2: mount controller, install 8 readers, terminate at doors | 2 techs, 7:30 AM–4:00 PM |
| 2 | Tue Nov 10, 2026 | Floor 3: mount controller, install 6 readers, terminate at doors | 2 techs, 7:30 AM–4:00 PM |
| 3 | Wed Nov 11, 2026 | Controller programming, badge enrollment, door function checks, customer walkthrough and sign-off | 2 techs, 7:30 AM–3:00 PM |

## Customer Prerequisites

Please review the items below with your facilities and IT teams and confirm with your Install Coordinator no later than 3 business days before the first install date.

Building management escort and access for the Keystone crew each install day from 7:30 AM, including loading dock and freight elevator.

Door hardware access: electrified strikes or maglocks installed at all controlled doors by the customer's door hardware contractor, with clear ceiling and wall access at each reader location.

Customer must have network drops and PoE switch ports active at all reader locations prior to install.

A dedicated 120V outlet within 6 ft of each controller location.

Badge holder list in CSV format (first name, last name, department, access group) sent to Keystone at least 5 days before install.

If prerequisites are not met on arrival, a $1,850 remobilization fee applies.

A customer IT contact available on Day 3 for controller network settings (IP addresses and VLAN).

A secure area on site to stage equipment overnight between install days.

## Warranty & Support

Hardware is covered for 3 years and labor for 1 year from customer sign-off. Service requests: support@keystone-access.example or 555-0147, Monday–Friday 7 AM–6 PM.

Questions about this schedule? Contact Teresa Vance at teresa.vance@keystone-access.example.